|  |
| --- |
| **San Joaquin Valley College - San Diego Campus** |
| **Dental Assisting Program – Timeline for Implementation** |
| **Activity** | **Initiate Activity** | **Complete Activity** |
| Investigate Dental Assisting (DA) Program feasibility for San Diego Campus  | November 1, 2011 | January 1, 2012 |
| Conduct feasibility study update | February 25, 2013 | March 20, 2013 |
| Seek Senior Management *Approval to Implement* | January 30, 2013 | January 30, 2013 |
| Establish facility design and equipment requirements | March 20, 2013 | April 8, 2013 |
| Prepare Budget Estimate | March 20, 2013 | April 1, 2013 |
| Prepare and submit application to Dental Board of California (DBC) | March 20, 2013 | July 31, 2013 |
| Prepare and submit ACCJC Substantive Change document | March 20, 2013 | October 7, 2013 |
| Receive DBC application approval *and* schedule initial site visit | September 16, 2013 |  October 25, 2013 |
| Hold DA Advisory Board meetings | August 15, 2013 | November 13, 2013 |
| Receive ACCJC approval to offer program | November 14, 2013 | November 14, 2013 |
| Recruit and hire DA faculty | December 1, 2013 | March 31, 2014 |
| Conduct admission and staff product knowledge training | December 1, 2013 | January 10, 2014 |
| Enter DA course schedules in CampusVue | December 1, 2013 | January 10, 2014 |
| Build-out and equip Dental Assisting (DA) clinical laboratories and classroom | November 20, 2013 | January 1, 2014 |
| Acquire DA library resources | January 1, 2014 | January 15, 2014 |
| Host on-site DBC accrediting visit to gain *Provisional Approval providing* permission to enroll students (To be scheduled)\* | February 1, 2014 | February 28, 2014 |
| Launch marketing | March 1, 2014 | March 1, 2014 |
| Conduct new faculty orientation | January 15, 2014 | January 21, 2014 |
| Orient DA Program students | March 28, 2014 | March 28, 2014 |
| Deliver DA Program first day of instruction | March 31, 2014 | March 31, 2014 |
| Notify all compliance agencies of program start | March 31, 2014 | April 11, 2014 |
| Move DA San Diego to standard internal review process | September 8, 2014 | September 8, 2014 |
| Evaluate and report on campus and program development process | September 8, 2014 | September 8, 2014 |
| Host DBC site visit prior to first cohort graduation | January 1, 2015 | January 15, 2015 |
| Graduate first cohort of DA students | February 8, 2015 | February 8, 2015 |
| Gain DBC *Full Board Approval* (Dental Board Meetings for 2015 to be scheduled)\* | June 1, 2015 | June 1, 2015 |
|  |  |  |
| \*Confirmed date to be determined. |  |  |